## Master Checklist
| # |  | Section in Tailings Guide | Management Action | Responsibility | Performance Measure | Schedule | References
Overarching Principles
Risk Assessment and Management
|  |  | 2.2.1 | Addressed below under Planning
BAT and BAP for Tailings Management
|  |  | 2.2.2 | Have the following factors been considering in selecting the tailings management technology for a specific tailings facility:
|  |  | 2.2.2 | • Are the likelihood or consequences of a failure of a tailings facility reduced?
|  |  | 2.2.2 | • Is material separation required to manage a potential geochemical concern?
|  |  | 2.2.2 | • How much water will be retained in the tailings during their transport and deposition?
|  |  | 2.2.2 | • Is there potential to place any tailings in mined-out areas?
|  |  | 2.2.2 | • Is the post-mining land use best served by a given technology?
|  |  | 2.2.2 | Has a rigorous decision-making tool such as multiple accounts analysis been used to select the most appropriate tailings management technology for a new facility, or to expand the capacity of an existing facility?
|  |  | 2.2.2 | Has a rigorous decision-making tool such as multiple accounts analysis been used to select the most appropriate location for a new tailings facility?
|  |  | 2.2.2 | In selecting the tailings management technology, have the potential risks of the alternatives assessed been considered across the life cycle of the facility, and have performance objectives and criteria been considered across the life cycle, including closure objectives?
|  |  | 2.2.2 | In selecting the tailings facility location, have the potential risks of the alternatives assessed been considered across the life cycle of the facility, and have performance objectives and criteria been considered across the life cycle, including closure objectives?
|  |  | 2.2.2 | Are best available/applicable practices for tailings management being implemented across the full spectrum of tailings management, including:
|  |  | 2.2.2 | • confirming geochemical and physical design parameters during the operations and ongoing construction, closure, and post-closure phases, and adjusting accordingly;
|  |  | 2.2.2 | • structural monitoring of tailings facilities to detect movement or change;
|  |  | 2.2.2 | • implementing a tailings management system;
|  |  | 2.2.2 | • implementing a system to identify and manage critical controls;
|  |  | 2.2.2 | • monitoring to assess performance against water balance requirements; and
|  |  | 2.2.2 | • conducting Independent Review.
Independent Review
|  |  | 2.2.3 | Has a mechanism been established for conducting Independent Review on a routine basis?
|  |  | 2.2.3 | Is Independent Review being implemented according to the established mechanism?
|  |  | 2.2.3 | Is Independent Review providing advice on:
|  |  | 2.2.3 | • completeness/appropriateness of the risk assessment and understanding;
|  |  | 2.2.3 | • effectiveness of tailings governance and the tailings management system;
|  |  | 2.2.3 | • whether the tailings facility is being effectively managed based on sound engineering practices;
|  |  | 2.2.3 | • whether the risk assessment and the acceptable level of risk should be reviewed and updated;
|  |  | 2.2.3 | • whether concepts and design criteria for the facility are consistent with regulatory requirements, industry guidelines and best practices, and current theory, methodologies and experience; and
|  |  | 2.2.3 | • areas for improvement in the management of the tailings facility.
|  |  | 2.2.3 | Is Independent Review being applied across all elements of the tailings management system, and across all phases of the life cycle of a tailings facility?
Designing and Operating for Closure
|  |  | 2.2.4 | Have long-term closure objectives and potential post-closure land uses been considered in the conceptual planning and design of the tailings facility?
|  |  | 2.2.4 | Has the tailings facility been designed to remain physically and chemically stable for the long-term.
|  |  | 2.2.4 | For older facilities not designed for closure, have options to adjust their tailings management practices or adopt newer technologies been considered to reduce risk and better position the tailings facility for closure?
|  |  | 2.2.4 | Is the tailing facility being constructed in a manner consistent with the closure objectives?
|  |  | 2.2.4 | Is the tailings facility being operated in a manner consistent with the closure objectives?
|  |  | 2.2.4 | Is the closure plan being updated, considering changes in the mine plan, regulatory changes, a changing risk profile of the tailings facility, status of progressive reclamation activities, and changes in COI expectations?
Policy and Commitment |  |  | Policy and Commitment
| 1 | -1 | 3 | Does the Owner have a demonstrated commitment to:
| 1 | -2 | 3 | • protection of public health and safety
| 1 | -3 | 3 | • responsible management of tailings with the objective of minimizing harm
| 1 | -4 | 3 | • allocation of appropriate resources to support tailings management activities; and
|  | -5 | 3 | • implementing a tailings management system through the actions of its employees, contractors and consultants
|  |  | 3 | On a facility-specific basis, has the Owner made more specific commitments to:
|  |  | 3 | • design, construct and operate tailings facilities in a manner that reduces long-term impacts, risks and liability;
|  |  | 3 | • ensure tailings management complies with regulatory requirements, and conforms with reasonable and prudent engineering practice, set design criteria, company standards/guidelines, and the Owner’s tailings management system;
|  |  | 3 | • engage with COI, taking into account their considerations in relation to the design (including location), operation, and management of the tailings facility;
|  |  | 3 | • manage the tailings facility commensurate with the risks it poses through implementation of BAT and BAP, with the objective of minimizing harm, and meeting performance, corporate governance, environmental and social requirements;
|  |  | 3 | • manage all solids and water within designated areas;
|  |  | 3 | • establish an ongoing program of review, including Independent Review, and continual improvement of health, safety and environmental performance through the management of risks associated with the tailings facility; and
|  |  | 3 | • implement the level of accountability, authority and competency for decision making appropriate to the level of risk that the decision entails.
|  |  | 3 | Are the policy and/or commitments:
|  |  | 3 | • approved by senior management and endorsed at the governance level;
|  |  | 3 | • communicated to employees;
|  |  | 3 | • understood by employees and contractors whose duties, either directly or indirectly, may affect the safety of tailings facilities; and
|  |  | 3 | • implemented with budget allocation?
Planning
Risk Assessment |  |  | Risk Management
|  |  | 4.1 | Is a risk management process in place for the tailings facility?
| 2 | -1 | 4.1 | Are risk assessments completed and/or updated at a frequency that supports the aims of the tailings management activities for that facility?
|  |  | 4.1 | Have the outcomes of the risk assessment been documented?
|  |  | 4.1 | Do the risk assessment and management measures take into account:
|  |  | 4.1 | • physical and chemicals risk of the tailings facility;
|  |  | 4.1 | • environmental risks such as earthquakes, landslides or avalanches, which could impact the facility; and
|  |  | 4.1 | • other risks external to the Owner and the facility, including regulatory and permitting risks (e.g., not obtaining permits in a timely manner, or permits that are not aligned with the design intent of the tailings facility).
| 2 | -2 | 4.1 | Has a risk management plan been prepared and documented that describes mitigation measures to:
|  |  | 4.1 | • eliminate or avoid risk to the extent practicable;
|  |  | 4.1 | • reduce risk by minimizing the likelihood or potential consequence of an unwanted event or condition that poses a risk; and,
|  |  | 4.1 | • detect, respond to, and minimize the consequences if an unwanted event or condition occurs that poses a risk?
|  |  | 4.1 | For a new tailings facility or the expansion of the capacity of an existing facility, has development of a conceptual risk management plan begun at the project conception and planning phase of the life cycle?
|  |  | 4.1 | For a new tailings facility or the expansion of the capacity of an existing facility, has the conceptual risk management plan been refined and developed in greater detail during the design phase?
| 2 | -3 | 4.1 | Is the risk management documentation, including the risk assessment record, reviewed and updated as necessary in the event of any changes not anticipated at the beginning of mine life (e.g. mine life extensions, suspensions to care and maintenance, re-starts, and process and technology changes)?
Performance Objectives |  |  | Performance Objectives
| 2 | -6 | 4.2 | Have performance objectives and criteria been developed that are aligned with the Owner's tailings management system, policy and/or commitments, standards/guidelines, regulatory requirements, commitments to COIs, and sound engineering and environmental practices?
|  |  | 4.2 | Are performance objectives, indicators, and associated performance measures for the tailings facility based on:
|  |  | 4.2 | • environmental requirements;
|  |  | 4.2 | • risk assessment and the level of acceptable impact and risk; and
|  |  | 4.2 | • risk management plan?
| 2 | -7 | 4.2 | Have performance objectives and criteria been developed for the entire life cycle of the tailings facility, including planning for both potential temporary and eventual permanent closure, and including:
| 2 | -8 | 4.2 | • protection of employee and public health and safety;
|  |  | 4.2 | • design objectives and criteria, including geotechnical, geochemical, operational, community, and environmental performance objectives that the tailings facility is expected to achieve;
| 2 | -9 | 4.2 | • mitigation of negative environmental impacts by ensuring continued physical and chemical stability of all components/structures; and,
|  |  | 4.2 | • acceptable post-closure use within a feasible technical and economic framework?
|  |  | 4.2 | For a new tailings facility or the expansion of the capacity of an existing facility:
|  |  | 4.2 | • Have performance objectives been established early in the project conception and planning phase?
|  |  | 4.2 | • Did the assessments of alternatives for facility location and tailings management technology take these performance objectives into account?
Accountability and Responsibility
|  |  | 4.3 | Do personnel with accountability and responsibility for tailings management have an understanding, appropriate to their accountability and responsibly, of how the tailings facility is designed, constructed and operated, including risk posed by the facility, the risk management plan, critical controls management, and operational constraints?
|  |  | 4.3 | Are accountabilities, responsibilities, and roles defined and documented for:
|  |  | 4.3 | • Owner’s Board of Directors or Governance Level;
|  |  | 4.3 | • Accountable Executive Officer;
|  |  | 4.3 | • Responsible Person(s);
|  |  | 4.3 | • Engineer of record; and
| 2 | -10 | 4.3 | • Independent Reviewer?
Management Process
Conformance Management
| 2 | -11 | 4.4.1 | Do conformance management processes ensure that:
| 2 | -12 | 4.4.1 | • applicable regulations, permits and commitments (including commitment/conditions coming from environmental assessment and permitting) are identified, documented, understood and effectively communicated;
| 2 | -13 | 4.4.1 | • Owner’s policies, guidelines, standards, practices are identified, documented, implemented, and reviewed;
| 2 | -14 | 4.4.1 | • those accountable and responsible for conformance understand their duties and have the necessary training and competence; and
| 2 | -16 | 4.4.1 | • processes to assess the state of conformance have been established, documented and communicated as required?
|  |  | 4.4.1 | In cases of non-conformance, did the Owner:
|  |  | 4.4.1 | • report the non-conformance, internally and externally, as appropriate;
|  |  | 4.4.1 | • determine the causes of the non-conformance, and identify and implement corrective measures;
|  |  | 4.4.1 | • address consequences of the non-conformance, including mitigating environmental impacts;
|  |  | 4.4.1 | • review the effectiveness of measures to correct the non-conformance; and
| 2 | -17 | 4.4.1 | • make necessary changes to the tailings management system to prevent future non-conformance?
Change Management |  |  | Change Management
| 2 | -18 | 4.4.2 | Have change management processes been documented and implemented to maintain the integrity of the tailings facility and the management system, including changes to:
| 2 | -19 | 4.4.2 | • approved designs and plans, including temporary changes, and expansions to the tailings facility;
|  |  | 4.4.2 | • facility ownership;
| 2 | -20 | 4.4.2 | • employees, contractors and consultants with key duties related to the tailings facility, including the Accountable Executive Officer, Responsible Person, operating and maintenance personnel, roles and responsibilities, including those of the EoR and Independent Reviewers;
| 2 | -21 | 4.4.2 | • conditions that may impact the ongoing operation/maintenance of the tailings facility, including temporary suspension of mining operations;
| 2 | -22 | 4.4.2 | • the closure plan;
| 2 | -24 | 4.4.2 | • regulatory requirements; and
| 2 | -25 | 4.4.2 | • any other changes that are potentially material to the risks associated with the tailings facility and its management (i.e., any change that has the potential to change the performance or risk profile of the tailings facility or any of its component parts).
|  |  | 4.4.2 | Do change management processes include succession planning for key roles related to tailings management, including the Responsible Person(s), EoR, and Independent Reviewers?
| 2 | -26 | 4.4.2 | Are changes which could impact the risk profile of the tailings facility reviewed and are potential impacts evaluated?
| 2 | -27 | 4.4.2 | Are changes which could impact the risk profile of the tailings facility approved by all the relevant persons (e.g., EoR, Responsible Person(s), personnel involved in tailings management and related activities, and the Accountable Executive Officer) as appropriate?
Controls |  |  | Controls
Critical Controls
| 2 | -29 | 4.4.3 | Has the Owner implemented processes to manage critical controls, including:
| 2 | -30 | 4.4.3 | • identifying potential failure modes and causes using risk assessment techniques;
| 2 | -31 | 4.4.3 | • identifying risk controls associated with potential failure modes and causes;
| 2 | -32 | 4.4.3 | • identifying those risk controls deemed to be critical on an Owner or facility-specific basis;
| 2 | -33 | 4.4.3 | • appointing a “risk owner” and “critical control owner” for that risk;
| 2 | -34 | 4.4.3 | • defining the critical controls and their performance criteria, measurable performance indicators, and surveillance requirements;
| 2 | -36 | 4.4.3 | • identifying pre-defined actions to be executed if control is lost;
| 2 | -37 | 4.4.3 | • verifying execution of critical controls by the critical control owner or designate, at a frequency commensurate with the frequency of control execution;
| 2 | -38 | 4.4.3 | • reporting deficiencies in critical controls to the Responsible Person(s) and, where appropriate, the Accountable Executive Officer, and identifying actions to address those deficiencies;
| 2 | -39 | 4.4.3 | • tracking implementation of actions to address critical control deficiencies, and reporting to the Responsible Person(s) and, where appropriate, the Accountable Executive Officer; and
| 2 | -40 | 4.4.3 | • periodically reviewing and updating risk controls and critical controls, based on updated risk assessments, risk management plans, and past performance?
Quality Management
|  |  | 4.4.3 | Has a quality management plan, or separate quality assurance and quality control plans been developed in implemented?
|  |  | 4.4.3 | Does quality management address an appropriate range of aspects related to the tailings facility, including construction, operation, maintenance and surveillance practices through the life of the facility?
Operational Controls
|  |  | 4.4.3 | Has an operation, maintenance and surveillance (OMS) manual been developed?
|  |  | 4.4.3 | Does the OMS manual document and clearly communicate responsible operating practices to operators and staff responsible for the tailings facility?
|  |  | 4.4.3 | Does the OMS manual include or refer to plans specific to key aspects of the operation of the tailings facility, including:
|  |  | 4.4.3 | • tailings transport and deposition plan;
|  |  | 4.4.3 | • water management plan; and
|  |  | 4.4.3 | • closure plan.
|  |  | 4.4.3 | Does the OMS manual describe risk controls and critical controls, together with associated performance criteria and indicators, and descriptions of actions to be taken if control is lost?
|  |  | 4.4.3 | Does the OMS manual document facility-specific performance measures as indicators of progress on management actions and objectives?
Resources and Scheduling |  | Resources | Resources
| 2 | -41 | 4.4.4 | Has the Owner identified, secured and regularly reviewed the adequacy of:
| 2 | -42 | 4.4.4 | • human resources and external contractors;
| 2 | -43 | 4.4.4 | • condition, function and suitability of equipment;
|  |  | 4.4.4 | • financial resources; and
| 2 | -45 | 4.4.4 | • schedules of activities that integrate the required resources related to tailings management?
Financial Control |  |  | Financial Control
| 2 | -46 | 4.4.4 | Has a budget for tailings management been established and documented that considers both short-term and long-term needs for effective tailings management throughout the life cycle?
| 2 | -48 | 4.4.4 | Has budget approval been obtained?
Control of Documented Information |  |  | Control of Documented Information
| 2 | -50 | 4.4.4 | Has the Owner established and implemented a process to ensure that documented information is created, maintained, retained, and archived?
|  |  | 4.4.4 | Has a process been developed and implemented to identify records related to the tailings facility that should be retained?
Training and Competence |  |  | Training and Competence
| 2 | -51 | 4.4.4 | Has a training program for relevant employees, contractors and/or consultants been developed and implemented?
| 2 | -52 | 4.4.4 | Are records for training for employees, contractors or consultants that is funded by or provided by the Owner maintained?
Communications |  |  | Communications
| 2 | -54 | 4.4.4 | Have communications processes been established and implemented to report significant information and decisions to senior management, the Engineer-of-Record, regulators and COIs, as appropriate?
Implementing the Tailings Management Framework
Operation, Maintenance and Surveillance Manual
|  |  | 5.1 | Has the OMS manual been implemented?
|  |  | 5.1 | Is the OMS manual regularly reviewed and revised, as appropriate, throughout the operations and ongoing construction phase of the tailings facility's life cycle, as well as beyond?
Emergency Preparedness and Response Plans
|  |  | 5.2 | Has an emergency preparedness and response plan (EPRP) been developed and documented that:
|  |  | 5.2 | • identifies possible emergency situations that could occur during the initial construction, operation and ongoing construction, closure, and post-closure phases of the life cycle of the tailings facility, and which could pose a risk to populations, infrastructure, and the environment; and
|  |  | 5.2 | • describes measures to respond to emergency situations and to prevent and mitigate on and off-site environmental and safety impacts associated with emergency situations.
|  |  | 5.2 | Is the EPRP for the tailings facility integrated with the overall site-level EPRP?
|  |  | 5.2 | If the tailings facility impounds water has an inundation study been conducted, and does the EPRP include inundation considerations?
|  |  | 5.2 | Are the OMS manual and the EPRP be aligned, such that there are no functional gaps between normal operations and emergency response, and that procedures are in place to transition from normal conditions to an emergency situation that may arise?
|  |  | 5.2 | Are procedures established and implemented for periodic review and testing of the EPRP, to ensure that the plan is current and that it is adequate in the event that an emergency occurs?
|  |  | 5.2 | Does review and testing of the EPRP involve potentially affected COI, such as local first responders and relevant government agencies?
|  |  | 5.2 | Have copies of the EPRP been provided to potentially affected COI?
Performance Evaluation |  |  | Performance Evaluation
| 2 | -1 | 6 | Do performance evaluations include results of inspections and reviews (both internal and independent) and address:
| 2 | -2 | 6 | • operating performance against objectives and critical controls;
| 2 | -3 | 6 | • compliance with regulatory requirements, and conformance with plans and commitments;
| 2 | -4 | 6 | • the risk management process, including the need to update the risk assessment;
| 3 | -13 | 6 | • need for changes or updates to the OMS manual, including evaluating the effectiveness of surveillance processes and the utility of the information being collected, and identifying any gaps in information collection; and
| 3 | -14 | 6 | • need for changes or updates to emergency preparedness and response plans?
| 3 | -15 | 6 | Do performance evaluations include the identification of gaps, deficiencies or areas of non-conformance with the tailings management system, including performance objectives and plans to address those objectives?
| 3 | -17 | 6 | Are results and recommendations of performance evaluations documented and reported to the Responsible Person(s), the Accountable Executive Officer and the Board of Directors or Governance Level, at a pre-defined frequency and level of detail?
Management Review for Continual Improvement |  |  | Management Review for Continual Improvement
| 3 | -26 | 7 | Has an annual review of tailings management been conducted to:
| 3 | -27 | 7 | • review the status of actions from the previous management review; and
| 3 | -28 | 7 | • review the overall performance of the tailings management system to ensure its continuing suitability, adequacy and effectiveness, and the need for changes to components of the system:
|  |  | 7 | → policy and commitment;
|  |  | 7 | → accountability and responsibilities;
|  |  | 7 | → conformance management;
|  |  | 7 | → change management;
|  |  | 7 | → controls: critical controls and quality management;
|  |  | 7 | → resources: financial controls, control of documented information, training and competence, and communications;
| 3 | -29 | 7 | • review performance of the tailings facility;
• effectiveness of risk management; and
| 3 | -30 | 7 | • adequacy of resources (human and financial) committed to tailings management?
| 3 | -34 | 7 | Does the management review process include identification and evaluation of the potential significance of any changes since the previous management review that are relevant to the tailings management system, including:
| 3 | -35 | 7 | • changes to regulatory requirements, standards and guidance, industry best practice, and commitments to COIs;
| 3 | -36 | 7 | • changes in mine operating conditions (e.g., production rate) or site environmental conditions;
| 3 | -37 | 7 | • changes outside the mine property that may influence the nature of potential impacts to or of the tailings facility; and
| 3 | -38 | 7 | • changes in the risk profile of the tailings facility?
| 3 | -39 | 7 | Does the management review provide a summary of significant issues related to the overall performance of the tailings facility and tailings management system, updated since the previous management review, that includes:
| 3 | -40 | 7 | • regulatory compliance, conformance with standards, policies and commitments, and status of any corrective actions;
| 3 | -41 | 7 | • facility maintenance;
| 3 | -42 | 7 | • tailings facility surveillance; and,
| 3 | -43 | 7 | • inspections, internal or external audits, evaluations of effectiveness, and independent reviews?
| 3 | -44 | 7 | Are the outcomes of the management review documented and does it include:
| 3 | -45 | 7 | • conclusions regarding the performance of the tailings facility and the tailings management system;
| 3 | -46 | 7 | • action plans to address findings contained in the conclusions, including:
| 3 | -47 | 7 | → actions to ensure performance objectives are met;
| 3 | -48 | 7 | → actions to address non-conformity with requirements, standards, policy, or commitments; and
| 3 | -49 | 7 | → opportunities for continual improvement?
| 3 | -50 | 7 | • modifications required in the tailings management system; and
| 3 | -51 | 7 | • enhancements to human and financial resources to help ensure effective tailings management?
Assurance
|  |  | 8 | Have assurance processes been implemented to provide an oversight process to ensure that tailings management is being effectively executed?
|  |  | 8 | Have the outcomes of assurance activities been considered in the Management Review for Continual Improvement?
Audits
|  |  | 8 | Has an internal audit been conducted to provide a formal, systematic and documented examination of the tailings facility’s conformance with prescribed criteria, legal requirements, and the Owner’s tailings management system?
|  |  | 8 | Has an external audit been conducted?
Evaluation of Effectiveness
|  |  | 8 | Has an evaluation of been conducted to assess whether the tailings management system (or components thereof) is achieving the intended results?
|  |  | 8 | In establishing the scope of the evaluation of effectiveness, have the following been considered:
|  |  | 8 | • changes in external conditions that could affect the system and achievement of established objectives; and
|  |  | 8 | • changes in internal conditions that could affect the system and achievement of established objectives?
|  |  | 8 | Have to following performance results and trends been evaluated to determine the effectiveness of the management system and its implementation:
|  |  | 8 | • the extent to which objectives and targets are being achieved;
|  |  | 8 | • the extent to which planned activities have been implemented as intended;
|  |  | 8 | • fulfilment of conformance obligations;
|  |  | 8 | • non-conformities and corrective actions based on inspection and audit results;
|  |  | 8 | • monitoring and measurement results;
|  |  | 8 | • adequacy of resources to support achievement of objectives;
|  |  | 8 | • feedback from practitioners and end users; and
|  |  | 8 | • any additional relevant information or feedback from COI.
Indpendent Review
|  |  | 8 | Addressed above under Overarching Principles