## Crisis MNGT & Communication
Towards Sustainable Mining - Action Plan 2025-2026 | [5 empty] | Last update: | 2025-12-18
Protocol | Site | Description | Action | Owner | Dateline | Action Conducted or Status | Status
Crisis Management | Corporate | There is no corporate-level crisis management or communications plan in place. | Complete corporate crisis management plan for the Toronto Corporate office | Corporate | 2026-12-31 | 0%
Crisis Management | Corporate | No CEO endorsement or documented risk reviews, no formal protocols, no Corporate Crisis Management Team or controlled plan, no trained media spokesperson, no stakeholder contact system, no equipped crisis center, and no formal employee alert/update mechanisms. | Complete corporate crisis management plan for the Toronto Corporate office | Corporate | 2026-12-31 | 0%
Crisis Management | Corporate | There is no tabletop crisis simulation at corporate level. | Complete corporate crisis management plan for the Toronto Corporate office | Corporate | 2026-12-31 | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Safe, Healthy, Respectful Work
Towards Sustainable Mining - Action Plan 2025-2026 | [5 empty] | Last update: | 2025-12-18
Protocol | Site | Description | Action | Owner | Dateline | Action Conducted or Status | Status
Safe, Healthy, and Respectful Workplaces | Fox Complex | Improvements are needed to cover all aspects of a comprehensive Industrial Hygiene program. | Dedicated resource for this purpose would be assigned by early 2026. | Marissa Stringer | 2026-04-15 | 0%
Safe, Healthy, and Respectful Workplaces | Fox Complex | No formal training program on Mental Health has been provided. | Review Mental Health Training options to implement. | Tyler Neeley Jean Leroux | 2026-10-31 | 0%
Safe, Healthy, and Respectful Workplaces | Fox Complex | Lack of identification of psychosocial hazards and the assessment of psychosocial risks. | Get third party support to create workplace phychosocial risk assessment | Tyler Neeley Jean Leroux | 2026-10-31 | 0%
Safe, Healthy, and Respectful Workplaces | Fox Complex | Observation and engagement program for psychological safety and respectful behaviour used the Zero Harm Safety Card, a daily health questionnaire completed by each Supervisor and employee. However, the program should be strengthened through a better integration of observed findings in mental-health training to ensure that identified issues are included in targeted training and prevention actions. | Add mental health check in Zero Harm Card. Supervisors to be trained as per mental health first aid training. | Tyler Neeley Jean Leroux | 2026-12-31 | 0%
Safe, Healthy, and Respectful Workplaces | Fox Complex | Data on the number and types of reported psychological safety and respectful-behavior issues should be systematically collected, monitored and analysed. | Contact EAP program administrator for opportunity to receive these statistics | Tyler Neeley Jean Leroux | 2026-10-31 | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Equitable, Diverse, Inclusive W
Towards Sustainable Mining - Action Plan 2025-2026 | [5 empty] | Last update: | 2025-12-18
Protocol | Site | Description | Action | Owner | Dateline | Action Conducted or Status | Status
Equitable, Diverse and Inclusive Workplaces | Corporate | EDI commitments at the corporate level should be established, formalized in policies, and communicated in all sites. | Implement Policy for EDI | Corporate | 2026-12-31 | 0%
Equitable, Diverse and Inclusive Workplaces | Corporate | EDI processes should be established and involve underrepresented groups. Must include clear roles and responsibilities. Must include a review of existing procedures to ensure the absence of bias in recruiting, promotion and training methods. | Implement Policy for EDI, including roles and responsibilities. | Corporate | 2026-12-31 | 0%
Equitable, Diverse and Inclusive Workplaces | Corporate | A process to collect and publish data illustrating workforce diversity should be established involving underrepresented groups and include diverse perspectives. | Review plan with corporate on implementing a process for collecting information on a diverse workplace. | Corporate | 2026-12-31 | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Indigenous & Community Relation
Towards Sustainable Mining - Action Plan 2025-2026 | [5 empty] | Last update: | 2025-12-18
Protocol | Site | Description | Action | Owner | Dateline | Action Conducted or Status | Status
Indigenous & Community Relationships | Corporate | There is no company-wide process to identify all COIs for the Black Fox Complex sites. | Implement process for identification of Communities of Interest. | Corporate | 2026-12-31 | 0%
Indigenous & Community Relationships | Corporate | Processes must be made available to the concerned COIs and reports on engagements must be published. | Implement process for identification of Communities of Interest. | Corporate | 2026-12-31 | 0%
Indigenous & Community Relationships | Corporate | The development of an engagement process with COIs to identify, prioritize and avoid actual or potential risks from activities is required. | Implement process for identification of Communities of Interest. | Corporate | 2026-12-31 | 0%
Indigenous & Community Relationships | Corporate | Risk prioritization must consider: Social aspects of the BlackFox Complex’s presence. | Review social risks for BlackFox Complex. | Corporate | 2026-12-31 | 0%
Indigenous & Community Relationships | Corporate | An action plan addressing prioritized impacts with established objectives and targets must be developed. | Implement process for identification of Communities of Interest. | Corporate | 2026-12-31 | 0%
Indigenous & Community Relationships | Corporate | A feedback process must be developed and communicated to COIs. It should allow: Receiving and addressing complaints, Responding to complaints within defined timelines, Logging complaints, Tracking the actions taken | Implement process for identification of Communities of Interest. | Corporate | 2026-12-31 | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Climate Change
Towards Sustainable Mining - Action Plan 2025-2026 | [5 empty] | Last update: | 2025-12-18
Protocol | Site | Description | Action | Owner | Dateline | Action Conducted or Status | Status
Climate Change | Corporate | McEwen Mining has not presented a corporate GHG reduction strategy.Targeted, time-bound actions were not provided. | Develop Green House Gas reduction strategy | Corporate | 2026-12-31 | 0%
Climate Change | Corporate | Climate change impact risks are not being considered. | Create risks assessment on climate change impact. | Corporate | 2026-12-31 | 0%
Climate Change | Corporate | Green House Gas awareness training is not provided to key personnel | Training on GHG awareness to employees. | Corporate | 2026-12-31 | 0%
Climate Change | Corporate | A comprehensive analysis of climate change impacts has not been carried out. Not considered in activities in general. | Create risks assessment on climate change impact. | Corporate | 2026-12-31 | 0%
Climate Change | Corporate | There is no medium- or long-term strategy to reduce GHG emissions. No defined milestones. | Develop Green House Gas reduction strategy | Corporate | 2026-12-31 | 0%
Climate Change | Corporate | Climate change risks have not been identified or communicated. | Create risks assessment on climate change impact. | Corporate | 2026-12-31 | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Water Management
Towards Sustainable Mining - Action Plan 2025-2026 | [5 empty] | Last update: | 2025-12-18
Protocol | Site | Description | Action | Owner | Dateline | Action Conducted or Status | Status
Water Management | Corporate | No senior management documented commitment to water stewardship. | Review Environment Policy and include commitment to water stewardship | Corporate | 2026-12-31 | 0%
Water Management | Corporate | Corporate policy lacks any water-specific language, responsibilities or resourcing. | Review Environment Policy and include commitment to water stewardship | Corporate | 2026-12-31 | 0%
Water Management | Corporate | Responsibilities for water management across the facility should be more specifically defined and assigned. | Review Environment Policy and include commitment to water stewardship, and roles and responsibilities | Corporate | 2026-12-31 | 0%
Water Management | Corporate | A general list of COIs has been compiled but lacks stakeholders with water-specific interests. | Implement process for identification of Communities of Interest. | Corporate | 2026-12-31 | 0%
Water Management | Corporate | While Environmental effects monitoring (EEM) /Habitat aquatic assessments and baseline studies exist for permitting (for the mill part), there is no clear assessment demonstrating how the facility’s operational water management practices contribute to cumulative effects in the watershed. A watershed-scale cumulative-effects evaluation tied to operations is required. | Conduct watershed scale cumulative effects evaluation | Corporate | 2026-12-31 | 0%
Water Management | Corporate | No public report for facility water performance against targets. Relevant data is available only through the national release inventory, not via facility‑level disclosures. | Release relevant data to facility level. | Corporate | 2026-12-31 | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Tailings Management
Towards Sustainable Mining - Action Plan 2025-2026 | [5 empty] | Last update: | 2025-12-18
Protocol | Site | Description | Action | Owner | Dateline | Action Conducted or Status | Status
Tailings Management | Corporate | Tailings management commitments have not been adopted or formalized in a policy. | Review policies and make appropriate modifications | Corporate | 2026-12-31 | 0%
Tailings Management | Fox Complex | An internal audit using the 2022 conformance table should be carried out. | Conduct internal audit | Ryan Cox | 2026-12-31 | 0%
Tailings Management | Corporate | An ERP and an EPP specific to tailings that meet all requirements of Guide v3.2 should be prepared. | Complete ERP and EPP | Corporate | 2026-12-31 | 0%
Tailings Management | Corporate | OSM manual does not meet all the criteria in the OSM Guide. | Audit OSM manual, and idenfiy deficiencies vs the guide. | Corporate | 2026-12-31 | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Biodiversity
Towards Sustainable Mining - Action Plan 2025-2026 | [5 empty] | Last update: | 2025-12-18
Protocol | Site | Description | Action | Owner | Dateline | Action Conducted or Status | Status
Biodiersity | Corporate | No specific commitment toward biodiversity in the Environmental Policy. | Review Policies and update to include commitment to biodiversity, | Corporate | 2026-12-31 | 0%
Biodiersity | Corporate | Demonstrating the senior management’s commitment toward biodiversity. It should be consistent with the intent of the TSM Mining and Biodiversity Conservation Framework. | Review Policies and update to include commitment to biodiversity, | Corporate | 2026-12-31 | 0%
Biodiersity | Corporate | Communicating the biodiversity commitment to relevant employees, contractors, and facility-level Communities of Interest (COI) | Post policy and update in high traffic areas. | Corporate | 2026-12-31 | 0%
Biodiersity | Corporate | Defining the roles, responsibilities, and accountability for the implementation of the commitment and making sure that resources have been assigned to support the implementation of the commitment. | Review Policies and update to include commitment to biodiversity, including roles and responsibilities | Corporate | 2026-12-31 | 0%
Biodiersity | Corporate | There is no facility-level biodiversity conservation plan or management system. | The absence of a facility-level plan or management system to address significant biodiversity aspects, implement the facility-level plan or management system and make sure it includes all the elements listed | Corporate | 2026-12-31 | 0%
Biodiersity | Corporate | There is no reporting regarding biodiversity. | Review data on biodiversity, make reports. | Corporate | 2026-12-31 | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%